## year 4
Name | Subitems | Owner | Status | Due date | Priority | Timeline - Start | Timeline - End | Dependency
Dissertation Proposal | Define Project scope and objectives | Julia Gongala | Done | 2023-10-10 | High | 2023-09-11 | 2023-09-29
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Define Project scope and objectives | Julia Gongala | Done | 2023-09-24 | 2023-10-10
Planning Phase | Create detailed Project Plan, Literature Review | Julia Gongala | Done | 2023-11-01 | High | 2023-10-12 | 2023-11-01 | Dissertation Proposal
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Create detailed Project Plan | Julia Gongala | Done | 2023-10-12 | 2023-10-17
| Literature Review |  | Done | 2023-10-19 | 2023-11-01
Interim Report | Background of Web Application Development, Front-End Technologies, Back-End Technologies, Python - Django and Flask, Preliminary Work, Current Progress and Future Work, Submission Deadline | Julia Gongala | Done | 2023-12-01 | Critical ⚠️️ | 2023-11-02 | 2023-12-01 | Planning Phase
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Background of Web Application Development | Julia Gongala | Done | 2023-11-03 | 2023-11-07
| Front-End Technologies | Julia Gongala | Done | 2023-11-09 | 2023-11-14
| Back-End Technologies | Julia Gongala | Done | 2023-11-14 | 2023-11-20
| Python - Django and Flask | Julia Gongala | Done | 2023-11-19 | 2023-11-22
| Preliminary Work | Julia Gongala | Done | 2023-11-23 | 2023-11-26
| Current Progress and Future Work | Julia Gongala | Done | 2023-11-27 | 2023-11-29
| Submission Deadline | Julia Gongala | Done | 2023-11-30 | 2023-11-30
Development in Flask | Set Up Flask Environment, Design Blog Structure, Implement Core Features, Testing and Debugging | Julia Gongala | Done | 2024-12-04 | High | 2023-12-11 | 2023-12-18 | Interim Report
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Set Up Flask Environment | Julia Gongala | Done | 2023-12-13 | 2024-03-21
| Design Blog Structure | Julia Gongala | Done | 2023-12-14 | 2024-03-21
| Implement Core Features | Julia Gongala | Done | 2023-12-16 | 2024-03-21
| Testing and Debugging | Julia Gongala |  | 2023-12-18 | 2024-03-21
Development in Django | Set Up Django Environment, Design Blog Structure, Implement Core Features, Testing and Debugging | Julia Gongala | Done | 2024-12-07 | High | 2024-01-01 | 2024-01-08 | Development in Flask
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Set Up Django Environment | Julia Gongala | Done | 2024-01-03 | 2024-01-03
| Design Blog Structure | Julia Gongala | Done | 2024-01-04 | 2024-01-04
| Implement Core Features | Julia Gongala | Done | 2024-01-06 | 2024-01-06
| Testing and Debugging | Julia Gongala | Done | 2024-01-08 | 2024-01-08
Presentation | Introduction - Why Python, Front - End, Front - End, Flask, Django, Compering frameworks, Advantages and disadvantages, When Flask, When Django | Julia Gongala | Done | 2024-02-26 | Critical ⚠️️ | 2024-01-22 | 2024-02-26 | Interim Report
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Introduction - Why Python | Julia Gongala | Done | 2024-01-22 | 2024-01-24
| Front - End | Julia Gongala | Done | 2024-01-25 | 2024-01-27
| Front - End | Julia Gongala | Done | 2024-01-29 | 2024-01-31
| Flask | Julia Gongala | Done | 2024-02-01 | 2024-02-03
| Django | Julia Gongala | Done | 2024-03-05 | 2024-03-07
| Compering frameworks | Julia Gongala | Done | 2024-03-08 | 2024-03-10
| Advantages and disadvantages | Julia Gongala | Done | 2024-02-13 | 2024-02-15
| When Flask | Julia Gongala | Done | 2024-02-17 | 2024-02-19
| When Django | Julia Gongala | Done | 2024-02-21 | 2024-02-23
Dissertation | Introduction, Front – End Development, Back – End Development, Full – Stack Development, Responsive Design, Security, Front - End Technologies, Back - End Technologies, Python, User-Centric Design and System Requirements, Comprehensive analysis, Advanced Blog, Conclusion | Julia Gongala | Done | 2024-03-28 | Critical ⚠️️ | 2024-01-20 | 2024-03-28 | Presentation
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Introduction | Julia Gongala | Done | 2024-01-20 | 2024-01-22
| Front – End Development | Julia Gongala | Done | 2024-01-24 | 2024-01-27
| Back – End Development | Julia Gongala | Done | 2024-01-25 | 2024-01-28
| Full – Stack Development | Julia Gongala | Done | 2024-01-29 | 2024-01-31
| Responsive Design | Julia Gongala | Done | 2024-02-02 | 2024-02-03
| Security | Julia Gongala | Done | 2024-02-03 | 2024-02-04
| Front - End Technologies | Julia Gongala | Done | 2024-02-05 | 2024-02-08
| Back - End Technologies | Julia Gongala | Done | 2024-02-12 | 2024-02-15
| Python | Julia Gongala | Done | 2024-02-19 | 2024-02-23
| User-Centric Design and System Requirements | Julia Gongala | Done | 2024-02-24 | 2024-02-25
| Comprehensive analysis | Julia Gongala | Done | 2024-02-26 | 2024-03-11
| Advanced Blog | Julia Gongala | Done | 2024-03-13 | 2024-03-24
| Conclusion | Julia Gongala | Done | 2024-03-25 | 2024-03-27
|  |  |  | 2023-10-10 to 2024-12-07 |  | 2023-09-11 | 2024-03-28
Apache Log Book - server side systems | Submission Deadline | Julia Gongala | Done | 2023-10-01 | High | 2023-09-17 | 2023-10-01
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2023-10-01 | 2023-10-01
Interface Design for Innovative Smart Devices - HCI & UX | Submission Deadline | Julia Gongala | Done | 2023-11-11 | High | 2023-10-17 | 2023-11-27
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2023-11-11 | 2023-11-11
Group Presentation - Internet Technologies | Submission Deadline | Julia Gongala | Done | 2023-10-31 | High | 2023-10-08 | 2023-10-31
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2023-10-31 | 2023-10-31
Critical Reflection - HCI & UX | Submission Deadline | Julia Gongala | Done | 2023-11-20 | High | 2023-10-10 | 2023-11-20
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2023-11-20 | 2023-11-20
Web App Design - Internet Technologies | Submission Deadline | Julia Gongala | Done | 2023-12-02 | High | 2023-11-12 | 2023-12-02
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2024-01-02 | 2024-01-02
Laravel Project and Blog - Server Side Systems | Submission Deadline | Julia Gongala | Done | 2023-12-05 | High | 2023-11-05 | 2023-12-05
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala | Done | 2023-12-05 | 2023-12-05
Dynamic Web Technologies - React App | Submission Deadline | Julia Gongala | Stuck | 2024-04-08 | High | 2024-03-18 | 2024-04-08
Subitems | Name | Owner | Status | Timeline - Start | Timeline - End
| Submission Deadline | Julia Gongala |  | 2024-04-08 | 2024-04-08
|  |  |  | 2023-10-01 to 2024-04-08 |  | 2023-09-17 | 2024-04-08