## TimelineGanttOverviewSection
Boards - Year 4 (by months)
|  |  | Sep-2023 | Sep-2023 | Sep-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Mar-2024 | Mar-2024 | Mar-2024 | Mar-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | May-2024 | May-2024 | May-2024 | May-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Oct-2024 | Oct-2024 | Oct-2024
| Start | End | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21
Dissertation Proposal | 11-Sep-2023 | 29-Sep-2023 | 11: Dissertation Proposal (11-Sep-23 - 29-Sep-23); 18: Dissertation Proposal (11-Sep-23 - 29-Sep-23); 25: Dissertation Proposal (11-Sep-23 - 29-Sep-23)
Apache Log Book - server side systems | 17-Sep-2023 | 01-Oct-2023 | 11: Apache Log Book - server side systems (17-Sep-23 - 01-Oct-23); 18: Apache Log Book - server side systems (17-Sep-23 - 01-Oct-23); 25: Apache Log Book - server side systems (17-Sep-23 - 01-Oct-23)
Group Presentation - Internet Technologies | 08-Oct-2023 | 31-Oct-2023 | 2: Group Presentation - Internet Technologies (08-Oct-23 - 31-Oct-23); 9: Group Presentation - Internet Technologies (08-Oct-23 - 31-Oct-23); 16: Group Presentation - Internet Technologies (08-Oct-23 - 31-Oct-23); 23: Group Presentation - Internet Technologies (08-Oct-23 - 31-Oct-23); 30: Group Presentation - Internet Technologies (08-Oct-23 - 31-Oct-23)
Critical Reflection - HCI & UX | 10-Oct-2023 | 20-Nov-2023 | 9: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 16: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 23: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 30: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 6: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 13: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23); 20: Critical Reflection - HCI & UX (10-Oct-23 - 20-Nov-23)
Planning Phase | 12-Oct-2023 | 01-Nov-2023 | 9: Planning Phase (12-Oct-23 - 01-Nov-23); 16: Planning Phase (12-Oct-23 - 01-Nov-23); 23: Planning Phase (12-Oct-23 - 01-Nov-23); 30: Planning Phase (12-Oct-23 - 01-Nov-23)
Interface Design for Innovative Smart Devices - HCI & UX | 17-Oct-2023 | 27-Nov-2023 | 16: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 23: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 30: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 6: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 13: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 20: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23); 27: Interface Design for Innovative Smart Devices - HCI & UX (17-Oct-23 - 27-Nov-23)
Interim Report | 02-Nov-2023 | 01-Dec-2023 | 30: Interim Report (02-Nov-23 - 01-Dec-23); 6: Interim Report (02-Nov-23 - 01-Dec-23); 13: Interim Report (02-Nov-23 - 01-Dec-23); 20: Interim Report (02-Nov-23 - 01-Dec-23); 27: Interim Report (02-Nov-23 - 01-Dec-23)
Laravel Project and Blog - Server Side Systems | 05-Nov-2023 | 05-Dec-2023 | 30: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23); 6: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23); 13: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23); 20: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23); 27: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23); 4: Laravel Project and Blog - Server Side Systems (05-Nov-23 - 05-Dec-23)
Web App Design - Internet Technologies | 12-Nov-2023 | 02-Dec-2023 | 6: Web App Design - Internet Technologies (12-Nov-23 - 02-Dec-23); 13: Web App Design - Internet Technologies (12-Nov-23 - 02-Dec-23); 20: Web App Design - Internet Technologies (12-Nov-23 - 02-Dec-23); 27: Web App Design - Internet Technologies (12-Nov-23 - 02-Dec-23)
Development in Flask | 11-Dec-2023 | 18-Dec-2023 | 11: Development in Flask (11-Dec-23 - 18-Dec-23); 18: Development in Flask (11-Dec-23 - 18-Dec-23)
Development in Django | 01-Jan-2024 | 08-Jan-2024 | 1: Development in Django (01-Jan-24 - 08-Jan-24); 8: Development in Django (01-Jan-24 - 08-Jan-24)
Dissertation | 20-Jan-2024 | 28-Mar-2024 | 15: Dissertation (20-Jan-24 - 28-Mar-24); 22: Dissertation (20-Jan-24 - 28-Mar-24); 29: Dissertation (20-Jan-24 - 28-Mar-24); 5: Dissertation (20-Jan-24 - 28-Mar-24); 12: Dissertation (20-Jan-24 - 28-Mar-24); 19: Dissertation (20-Jan-24 - 28-Mar-24); 26: Dissertation (20-Jan-24 - 28-Mar-24); 4: Dissertation (20-Jan-24 - 28-Mar-24); 11: Dissertation (20-Jan-24 - 28-Mar-24); 18: Dissertation (20-Jan-24 - 28-Mar-24); 25: Dissertation (20-Jan-24 - 28-Mar-24)
Presentation | 22-Jan-2024 | 26-Feb-2024 | 22: Presentation (22-Jan-24 - 26-Feb-24); 29: Presentation (22-Jan-24 - 26-Feb-24); 5: Presentation (22-Jan-24 - 26-Feb-24); 12: Presentation (22-Jan-24 - 26-Feb-24); 19: Presentation (22-Jan-24 - 26-Feb-24); 26: Presentation (22-Jan-24 - 26-Feb-24)
Dynamic Web Technologies - React App | 18-Mar-2024 | 08-Apr-2024 | 18: Dynamic Web Technologies - React App (18-Mar-24 - 08-Apr-24); 25: Dynamic Web Technologies - React App (18-Mar-24 - 08-Apr-24); 1: Dynamic Web Technologies - React App (18-Mar-24 - 08-Apr-24); 8: Dynamic Web Technologies - React App (18-Mar-24 - 08-Apr-24)